## Tabelle1
Initial
Open Story Points | Accomplished SP till now | Hours invested so far | Velocity so far
78 | 12 | 32 | 0.375
Product Burndown
Sprint | Planned Hours | SP change due to plan change | Accomplished story points in current sprint | Actual Hours | Open Story Points at Begin | Totally Accompl. SP at Begin | Actually accomplished SP at end. | Actual Hours so far at Begin | Open Story Points at End | Velocity (stpts / hour)
2020-02-24 | 28 |  | 3 | 34 | 78 | 0 | 3 | 0 | 75 | 0.088235
2020-03-09 | 20 |  | 2 | 24 | 75 | 3 | 5 | 34 | 73 | 0.086207
2020-03-23 | 32 |  | 0 | 40 | 73 | 5 | 5 | 58 | 73 | 0.05102
2020-04-06 | 28 |  | 0 | 0 | 73 | 5 | 5 | 98 | 73 | 0.05102
2020-04-20 | 18 |  | 2 | 20 | 73 | 5 | 7 | 98 | 71 | 0.059322
2020-05-04 | 28 |  | 3 | 40 | 71 | 7 | 10 | 118 | 68 | 0.063291
2020-05-18 | 24 |  | 3 | 24 | 68 | 10 | 13 | 158 | 65 | 0.071429
2020-06-01 | 24 |  | 0 | 0 | 65 | 13 | 13 | 182 | 65 | 0.071429
2020-06-15 | 24 |  | 0 | 0 | 65 | 13 | 13 | 182 | 65 | 0.071429
2020-06-29 | 24 |  | 0 | 0 | 65 | 13 | 13 | 182 | 65 | 0.071429
2020-07-13 | 0 |  | 0 | 0 | 65 | 13 | 13 | 182 | 65 | 0.071429
2020-07-27 | 0 |  | 0 | 0 | 65 | 13 | 13 | 182 | 65 | 0.071429
2020-08-10 | 0 |  | 0 | 0 | 65 | 13 | 13 | 182 | 65 | 0.071429
2020-08-24 | 0 |  | 0 | 0 | 65 | 13 | 13 | 182 | 65 | 0.071429
2020-09-07 | 24 |  | 0 | 0 | 65 | 13 | 13 | 182 | 65 | 0.071429
2020-09-21 | 24 |  | 12 | 40 | 65 | 13 | 25 | 182 | 53 | 0.11261
2020-10-05 | 24 |  | 6 | 13 | 53 | 25 | 31 | 222 | 47 | 0.13191
2020-10-19 | 24 |  | 5 | 15 | 47 | 31 | 36 | 235 | 42 | 0.144
2020-11-02 | 24 |  | 11 | 23 | 42 | 36 | 47 | 250 | 31 | 0.17216
2020-11-16 | 24 |  | 7 | 18 | 31 | 47 | 54 | 273 | 24 | 0.18557
2020-11-30 | 24 |  | 5 | 15 | 24 | 54 | 59 | 291 | 19 | 0.19281
2020-12-14 | 24 |  | 5 | 40 | 19 | 59 | 64 | 306 | 14 | 0.18497
2020-12-28 | 24 |  | 6 | 20 | 14 | 64 | 70 | 346 | 8 | 0.19126
2021-01-11 | 24 |  | 3 | 10 | 8 | 70 | 73 | 366 | 5 | 0.19415
2021-01-25 | 24 |  | 3 | 12 | 5 | 73 | 76 | 376 | 2 | 0.19588
2021-02-08 | 24 | 8 | 4 | 10 | 10 | 76 | 80 | 388 | 6 | 0.20101
2021-02-22 | 24 |  |  |  | 6 | 80 | 80 | 398 | 1.1759 | 0.20101
2021-03-08 | 24 |  |  |  | 1.1759 | 80 | 80 | 398 | 0 | 0.20101
2021-03-22 | 24 |  |  |  | 0 | 80 | 80 | 398 | 0 | 0.20101
2021-04-05 | 24 |  |  |  | 0 | 80 | 80 | 398 | 0 | 0.20101
2021-04-19 | 24 |  |  |  | 0 | 80 | 80 | 398 | 0 | 0.20101
2021-05-03 | 24 |  |  |  | 0 | 80 | 80 | 398 | 0 | 0.20101
2021-05-17 | 24 |  |  |  | 0 | 80 | 80 | 398 | 0 | 0.20101
2021-05-31 | 0 |  |  |  | 0 | 80 | 80 | 398 | 0 | 0.20101
2021-06-14 | 0 |  |  |  | 0 | 80 | 80 | 398 | 0 | 0.20101
2021-06-28 | 0 |  |  |  | 0 | 80 | 80 | 398 | 0 | 0.20101
2021-07-12 | 0 |  |  |  | 0 | 80 | 80 | 398 | 0 | 0.20101
2021-07-26 | 0 |  |  |  | 0 | 80 | 80 | 398 | 0 | 0.20101
2021-08-09 | 0 |  |  |  | 0 | 80 | 80 | 398 | 0 | 0.20101
2021-08-23 | 0 |  |  |  | 0 | 80 | 80 | 398 | 0 | 0.20101
2021-09-06 | 0 |  |  |  | 0 | 80 | 80 | 398 | 0 | 0.20101
2021-09-20 | 0 |  |  |  | 0 | 80 | 80 | 398 | 0 | 0.20101
2021-10-04 | 0 |  |  |  | 0 | 80 | 80 | 398 | 0 | 0.20101
2021-10-18 | 0 |  |  |  | 0 | 80 | 80 | 398 | 0 | 0.20101
2021-11-01 | 0 |  |  |  | 0 | 80 | 80 | 398 | 0 | 0.20101
2021-11-15 | 0 |  |  |  | 0 | 80 | 80 | 398 | 0 | 0.20101
| 514 |  | 3.0769 | 15.3077
Formulas:
Open Story Points = [Open Story Points, row above]+14